## Sheet1
Total	77.404,88 €					Social Security Taxes	28,30 %
Total (not including VAT)	63.970,97 €					Hardware amortization	48
				VAT	21,00 %
Members
Name	Role	Salary (1 month)	Salary (5 month)	Social Security Taxes	Total
Cantón Fernández, Adrián	Business management/Mobile application developer	1.800,00 €	9.000,00 €	3.552,30 €	12.552,30 €
Carpio Camacho, Daniel	Analyst/Front end developer	1.700,00 €	8.500,00 €	3.354,95 €	11.854,95 €
Fresno Aranda, Rafael	Backend developer/ API integration	1.400,00 €	7.000,00 €	2.762,90 €	9.762,90 €
Rebollo Lobo, Pablo	Project manager/Backend developer	2.000,00 €	10.000,00 €	3.947,00 €	13.947,00 €
Rodríguez Regidor, Juan	Requirements engineer/Backend developer	1.500,00 €	7.500,00 €	2.960,25 €	10.460,25 €
				Total:	58.577,41 €

Hardware
	Purchase price	Per month	Total (5 month)
Adrián Cantón Laptop	800,00 €	16,67 €	83,33 €
Daniel Carpio Laptop	800,00 €	16,67 €	83,33 €
Rafael Fresno Laptop	1.300,00 €	27,08 €	135,42 €
Pablo Rebollo Laptop	900,00 €	18,75 €	93,75 €
Juan Rodríguez Laptop	800,00 €	16,67 €	83,33 €
		Total:	479,17 €

Others	Per month (not including VAT)	5 months	Total (not including VAT)
Workplace (offices, internet, electricity…)	800,00 €	4.000,00 €	4.840,00 €
Risk	0,00 €	0,00 €	0,00 €
		Total:	4.840,00 €
Heroku deployment for one year
Per month	One year
6,20 €	74,40 €