## Optimista
Total	29.480,22 €					SS Taxes	28,30 %
Total without VAT	24.363,82 €					Amortization months	60
				VAT	21,00 %
				Hours per month	40
Team					Months	4
Name	Role	€/hour	€/month	€/Xmonths	Soc Sec,	Total
Cantón Fernández, Adrián	Business management/Full Stack Developer	20,80 €	832,00 €	3.328,00 €	1.313,56 €	4.641,56 €
Carpio Camacho, Daniel	Analyst/Front end developer	20,80 €	832,00 €	3.328,00 €	1.313,56 €	4.641,56 €
Fresno Aranda, Rafael	Backend developer/ API integration	20,80 €	832,00 €	3.328,00 €	1.313,56 €	4.641,56 €
Rebollo Lobo, Pablo	Project manager/Backend developer	20,80 €	832,00 €	3.328,00 €	1.313,56 €	4.641,56 €
Rodríguez Regidor, Juan	Requirements engineer/Backend developer	20,80 €	832,00 €	3.328,00 €	1.313,56 €	4.641,56 €
				Total	23.207,81 €

Hardware amortization
Piece of equipment	Adquisition price	Monthly amortization	Total
Adrián Cantón Laptop	800,00 €	13,33 €	53,33 €
Daniel Carpio Laptop	800,00 €	13,33 €	53,33 €
Rafael Fresno Laptop	1.300,00 €	21,67 €	86,67 €
Pablo Rebollo Laptop	900,00 €	15,00 €	60,00 €
Juan Rodríguez Laptop	800,00 €	13,33 €	53,33 €
		Total	306,67 €

Deployment
First year storage and hosting costs	669,34 €

Advertisement
Monthly	Total (6 months)
30,00 €	180,00 €

Risk prevention funds
Percentage of our budget	0,00 %
Total	0,00 €

## Realista_1
Total	30.514,18 €					SS Taxes	28,30 %
Total without VAT	25.218,33 €					Amortization months	60
				VAT	21,00 %
				Hours per month	40
Team					Months	4
Name	Role	€/hour	€/month	€/Xmonths	Soc Sec,	Total
Cantón Fernández, Adrián	Business management/Full Stack Developer	20,80 €	832,00 €	3.328,00 €	1.313,56 €	4.641,56 €
Carpio Camacho, Daniel	Analyst/Front end developer	20,80 €	832,00 €	3.328,00 €	1.313,56 €	4.641,56 €
Fresno Aranda, Rafael	Backend developer/ API integration	20,80 €	832,00 €	3.328,00 €	1.313,56 €	4.641,56 €
Rebollo Lobo, Pablo	Project manager/Backend developer	20,80 €	832,00 €	3.328,00 €	1.313,56 €	4.641,56 €
Rodríguez Regidor, Juan	Requirements engineer/Backend developer	20,80 €	832,00 €	3.328,00 €	1.313,56 €	4.641,56 €
				Total	23.207,81 €

Hardware amortization
Piece of equipment	Adquisition price	Monthly amortization	Total
Adrián Cantón Laptop	800,00 €	13,33 €	53,33 €
Daniel Carpio Laptop	800,00 €	13,33 €	53,33 €
Rafael Fresno Laptop	1.300,00 €	21,67 €	86,67 €
Pablo Rebollo Laptop	900,00 €	15,00 €	60,00 €
Juan Rodríguez Laptop	800,00 €	13,33 €	53,33 €
		Total	306,67 €

Deployment
First year storage and hosting costs	669,34 €

Advertisement
Monthly	Total (6 months)
50,00 €	300,00 €

Risk prevention funds
Percentage of our budget	3,00 %
Total	734,51 €

## Realista_2
Total	32.087,61 €					SS Taxes	28,30 %
Total without VAT	26.518,68 €					Amortization months	60
				VAT	21,00 %
				Hours per month	40
Team					Months	4
Name	Role	€/hour	€/month	€/Xmonths	Soc Sec,	Total
Cantón Fernández, Adrián	Business management/Full Stack Developer	20,80 €	832,00 €	3.328,00 €	1.313,56 €	4.641,56 €
Carpio Camacho, Daniel	Analyst/Front end developer	20,80 €	832,00 €	3.328,00 €	1.313,56 €	4.641,56 €
Fresno Aranda, Rafael	Backend developer/ API integration	20,80 €	832,00 €	3.328,00 €	1.313,56 €	4.641,56 €
Rebollo Lobo, Pablo	Project manager/Backend developer	20,80 €	832,00 €	3.328,00 €	1.313,56 €	4.641,56 €
Rodríguez Regidor, Juan	Requirements engineer/Backend developer	20,80 €	832,00 €	3.328,00 €	1.313,56 €	4.641,56 €
				Total	23.207,81 €

Hardware amortization
Piece of equipment	Adquisition price	Monthly amortization	Total
Adrián Cantón Laptop	800,00 €	13,33 €	53,33 €
Daniel Carpio Laptop	800,00 €	13,33 €	53,33 €
Rafael Fresno Laptop	1.300,00 €	21,67 €	86,67 €
Pablo Rebollo Laptop	900,00 €	15,00 €	60,00 €
Juan Rodríguez Laptop	800,00 €	13,33 €	53,33 €
		Total	306,67 €

Deployment
First year storage and hosting costs	669,34 €

Advertisement
Monthly	Total (6 months)
100,00 €	600,00 €

Risk prevention funds
Percentage of our budget	7,00 %
Total	1.734,87 €

## Pesimista
Total	34.486,68 €					SS Taxes	28,30 %
Total without VAT	28.501,39 €					Amortization months	60
				VAT	21,00 %
				Hours per month	40
Team					Months	4
Name	Role	€/hour	€/month	€/Xmonths	Soc Sec,	Total
Cantón Fernández, Adrián	Business management/Full Stack Developer	20,80 €	832,00 €	3.328,00 €	1.313,56 €	4.641,56 €
Carpio Camacho, Daniel	Analyst/Front end developer	20,80 €	832,00 €	3.328,00 €	1.313,56 €	4.641,56 €
Fresno Aranda, Rafael	Backend developer/ API integration	20,80 €	832,00 €	3.328,00 €	1.313,56 €	4.641,56 €
Rebollo Lobo, Pablo	Project manager/Backend developer	20,80 €	832,00 €	3.328,00 €	1.313,56 €	4.641,56 €
Rodríguez Regidor, Juan	Requirements engineer/Backend developer	20,80 €	832,00 €	3.328,00 €	1.313,56 €	4.641,56 €
				Total	23.207,81 €

Hardware amortization
Piece of equipment	Adquisition price	Monthly amortization	Total
Adrián Cantón Laptop	800,00 €	13,33 €	53,33 €
Daniel Carpio Laptop	800,00 €	13,33 €	53,33 €
Rafael Fresno Laptop	1.300,00 €	21,67 €	86,67 €
Pablo Rebollo Laptop	900,00 €	15,00 €	60,00 €
Juan Rodríguez Laptop	800,00 €	13,33 €	53,33 €
		Total	306,67 €

Deployment
First year storage and hosting costs	669,34 €

Advertisement
Monthly	Total (6 months)
100,00 €	600,00 €

Risk prevention funds
Percentage of our budget	15,00 %
Total	3.717,57 €